## Sheet1
MS 1 | Task |  | 2017-09-01 | 2017-09-08 | 2017-09-11 | Invidual Total
Will Kozel | Current environment, project background, problems with current system |  | 2 hours | 2 hours | 2 hours | 6 hours
Johann Quintero | System requirements, users involved in or affected by project |  | 2 hours | 2 hours | 2 hours | 6 hours
Paige Lowery | Company Background and Description, Expected benefits of proposed system, Scope |  | 2 hours | 2 hours | 2 hours | 6 hours
Jack Fentzke | System objectives, features, and constraints |  | 2 hours | 2 hours | 2 hours | 6 hours
|  | Total Per Meeting | 8 hours | 8 hours | 8 hours
|  | Overall | 24 hours
MS 2 | Task |  | 2017-09-14 | 2017-09-20 | 2017-09-23 | Invidual Total
Will Kozel | Proposed system objectives and restraints, fully detailed use case specifications |  | 1 hour | 2 hours | 3 hours | 6 hours
Johann Quintero | Stakeholders, use case executive summary, non-functional requirements |  | 2 hours | 1 hour | 2 hours | 5 hours
Paige Lowery | Executive background, current business enviroment, Expected benefits, organize Milestone 2 documents and deliverables |  | 1 hour | 1 hour | 3 hours | 5 hours
Jack Fentzke | Context diagram, use case diagram, |  | 2 hours | 1 hour | 3 hours | 6 hours
|  | Total Per Meeting | 6 hours | 5 hours | 11 hours
|  | Overall | 22 hours
MS 3 | Task |  | 2017-10-14 | 2017-10-15 | 2017-10-16 | Invidual Total
Group | Exec. Summary w/ Narrative & Conclusions |  | 1 hour
Paige | Complete DFD |  |  | 4 hours
Will | Detailed Non-Functional Requirements |  |  | 2 hours
Johann | Program Plan (With Logic & I/O's) |  | 2 hours
Will | Hardware and Software Specifications |  |  |  | 3 hours
Johann | Navigation Diagram |  |  | 3 hours
Jack | Mockup Forms and Reports |  | 4 hours
Jack and Will | Sample Reports w/ Data |  |  | 2 hours
Paige | Entity Relationship Diagram |  |  |  | 2 hours
Jack | Include Proper/Standard Naming Conventions
|  | Total Per Meeting | 7 hours | 11 hours | 5 hours
|  | Overall | 23 hours
MS 4 | Task |  | 2017-10-23 | 2017-10-24 | 2017-10-25 | Invidual Total
Group | Update use cases and additional documents |  | 1 hour | 2 hours
Paige | Presentation |  |  |  | 1 hour
Will | Updated use cases, Program Plan |  | 3 hours | 2 hours | 3 hours
Johann | Database, update navigation diagram |  | 2 hours | 1 hour | 1 hour
Jack | Interface, Program Plan |  | 3 hours | 2 hour | 3 hour
|  | Total Per Meeting | 8 hours | 5 hours | 8 hours
|  | Overall | 23 hours