## Sheet1
Component | Assigned To | Due Date
MS 1 - Conceptual Walkthrough | Group | 2017-09-13
Company Background | Group | 2017-08-27
Current Environment | Will | 2017-08-30
Reason for Selection | Will | 2017-08-30
Discussion of Problem | Will | 2017-08-30
System Obj. and Constraints | Jack | 2017-09-02
System Requirements | Johann | 2017-09-07
Expected Benefits | Paige | 2017-09-07
Stakeholders | Johann | 2017-09-10
Scope Discussion | Paige | 2017-09-10
Problem Analysis | Group | 2017-09-10
MS 2 - Analysis Presentation | Group | 2017-09-27
Additional Suggestions/Improvements/Changes | Group | 2017-09-14
Context Diagram (NOT THE DFD) | Jack | 2017-09-25
Use Cases | Jack, Johann, Will | 2017-09-23
Data Flow Diagram | Johann | 2017-09-26
Appropriate Elicitation to Gather Information | Will | 2017-09-20
Develop Requirement Documentation | Paige | 2017-09-22
Non-Functional Requirements Artifacts | Johann | 2017-09-21
Documentation Deliverables | Paige | 2017-09-25
MS 3 - Design Presentation | Group | 2017-10-18
Exec. Summary w/ Narrative & Conclusions | Group | 2017-10-17
Complete DFD | Paige | 2017-10-12
Detailed Non-Functional Requirements | Will | 2017-10-15
Program Plan (With Logic & I/O's) | Johann | 2017-10-14
Hardware and Software Specifications | Will | 2017-10-15
Navigation Diagram | Johann | 2017-10-14
Mockup Forms and Reports | Jack | 2017-10-15
Sample Reports w/ Data | Jack and Will | 2017-10-16
Entity Relationship Diagram | Paige | 2017-10-15
Include Proper/Standard Naming Conventions | Jack | 2017-10-15
MS 4 - Structured Walkthrough | Group | 2017-11-01
Database Development | Will | 2017-10-17
Program Development | Jack | 2017-10-20
Test Plan | Johann | 2017-10-25
Updated Project Plan and Timesheets | Paige | 2017-10-29
Milestone Evaluation | Group | 2017-11-01
MS 5 - Training Presentation | Group | 2017-11-15
Choice of Training Mode | Group | 2017-11-10
Narrative and Screen Shots from Presentation | Will | 2017-11-13
Documentation | Paige | 2017-11-13
Template for Training New Users | Jack and Johann | 2017-11-13
MS 6 - Final Presentation | Group | 2017-12-06
Updated Project Plan and Timesheets | Paige | 2017-12-01
Complete Training with users | Group | 2017-12-02
Final Presentation | Group | 2017-12-03
Group Member's Evaluations of the Project | Group | 2017-12-04
Final Testing of Program (Debugging) | Will | 2017-12-05
Updating Final Deliverables | Group | 2017-12-06